## Study Plan
Java Study and Project Schedule
Week- | Day | Date | Subject | Assessment
1 | Wednesday | 2021-01-27 | Java Programming: Java & AS Basics | Practice Problem
| Saturday | 2021-01-30 | Project Week 1 | Milestone 1
2 | Wednesday | 2021-02-03 | Java Basic: Variables, Conditional, Loops, & Methods. | Practice Problem
| Saturday | 2021-02-06 | Project Week 2 | Milestone 2
3 | Wednesday | 2021-02-10 | Java Programming: Class, Object, Inheritance & GUI. | Practice Problem
| Saturday | 2021-02-13 | Project Week 3 | Milestone 3
4 | Wednesday | 2021-02-17 | Java Programming: Mini App #1 | Practice Problem
| Saturday | 2021-02-20 | Project Week 4 | Milestone 4
5 | Wednesday | 2021-02-24 | Java Programming: Mini App #2 | Practice Problem
| Saturday | 2021-02-27 | Project Week 5 | Milestone 5
6 | Wednesday | 2021-03-03 | Java Programming: Mini App #2 | Practice Problem
| Saturday | 2021-03-06 | Project Week 6 | Milestone 6
7 | Wednesday | 2021-03-10 | Java Programming: Mini App #3 | Practice Problem
| Saturday | 2021-03-13 | Project Week 7 | Milestone 7
8 | Wednesday | 2021-03-17 | Java Programming: Mini App #3 | Practice Problem
| Saturday | 2021-03-20 | Project Week 8 | Milestone 8
Topic

## Tracker
PROJECT TRACKER
Milestones | Features | Completetion | Discussion | Next week target
Week 1 | Page 1: Login, Username, Password, forget password, Registration | design, proposal, timeline, log in code | selesain design logo, user interface (log in dan registration form) | sudah selesai semua yang ada di discussion
| Page 2: Registration (first and last name, gmail, DOB, POB, University -> year and faculty, gender, create password and re-confirm password |  |  | sudah selesai semua yang ada di discussion
| Page 3: Phone Verification |  |  | mulai nyicil untuk verifikasi no hp
| Page 4: Upload Kartu Mahasiswa |  |  | mulai nyicil untuk upload kartu mahasiswa
Page 5: Questionnaire (Dream company) - kasih list perusahaan yang kerja sama + skip button + search (Company)
Page 6: Questionnaire (Job) - kasih liat job list yang memungkinkan + skip button + search (Job)
Page 7: Home Page: Top: User profile (kiri), Logo (tengah), Search button (kanan) Body: (Atas) slide shows (iklan+content), (bawahny) course/job button, flash card (descibe: tutor's name, university, occuption, course, price), show all button Bottom: Home Button (tombol main page), Wishlist button , Shopping cart button, inbox button, calender button.
Page 8: Profile (Name, DOB, University -> year -> faculty, Gender, gmail, CV, History, save and cancel button
Page 9 : Big title, University logo, checklist, wishlist, what you will learn, instructors personal information, course length, effort, price, Institution, subject, level, language and course type
Page 10: Wishlist, find courses
Page 11: Shopping cart, start shopping
Page 12: Inbox, all courses, profile picture and name of the sender, title of the mail, message, date and time it was sent
Page 13: Calendar
Week 2 | 1/2 Coding Registration form | 1/2 Coding Registration form | selesain 1/2 coding registration form dan mulai + selesain log in page juga | Verifikasi no Hp dan Upload kartu mahasiswa harus udah mulai
Kalo bisa kelarin codingnya juga
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8